## Feb-2021
S.No	Task	Description	Estimation ( Hours)	Status	Developer Comment	Client Comment
1	Critical Control Panel Issues - Only Affects Some Users 0/2 completed	Media Drive- Some client have no access to the media drive - see video - Use MEG for diagnosing	8
2		Stigter Van Doesburg only - the Exhibition Table hangs when you first launch it	6
3	Control Panel - Issues - affect everyone 0/5 completed	Selected Art - User Profile - not possible to save the order of the artworks	4
4		Selected Art - in Managed Artist Profile - Network tab- not possible to save the order of the artworks - same issue as in user profile	12
5		Media Drive, Artists, Art, Exhibitions Table - the number under the table showing the number of tables that can be loaded is too high - allows you to click on links that crash	8
6		Control Panel - Languages Don't Save in user profile	4
7		Media Drive Root Page - Remove the adding folder to folder options in dropdown - or - have a better error message	3
8	Critical Showroom Issues - Only Affect Some Users 0/3 completed	Not all shorooms show the users' icon - use JASON in NEW - (you can also use MEG)	6
9		Not all showroom have exhibitions where they should - USE MEG for diagnostics	6
10		Showroom navigation is strange for some users	4
11	Showroom - small tweaks 0/5 completed	Make the showroom dynamic - not stattic	24
12		Restore the progressive web app experience (we lost it when we added the navigation.	6
13		Follow - page - change name to Follow/Contact	4
14		Follow/Contact page - tweak layout in desktop view - turn the desktop layout to single collumn - like linktr.ee	6
15		Add the following buttons to the follow contact page (see attached - (website, e-mail, directions)	4
16	Mnisite Exhibition Templates - Seoul - small bugs 0/1 completed	Bug on colours of circles Sold = Red ; Available = Green everything else = blank - (see video and details)	4
		Buffering	24
		Total Hours	133